Case Study on Preparation of a Software Project Plan

Covering Scope, Timeline, and Team Roles for a Sample Application

# Aim

To prepare a comprehensive software project plan — covering scope, timeline, and team roles — for a real-world software application, and to demonstrate how proper planning supports successful project execution.

# Objective

- Study the key components of a software project plan.

- Define the scope of a real-world software application.

- Develop a realistic project timeline with phases and milestones.

- Identify team roles and responsibilities required for execution.

- Recommend a resource allocation and risk management approach.

# Selected Software Application

## Online Learning Management System (e.g., Coursera/Udemy)

## Overview

An Online Learning Management System (LMS) allows students and instructors to:

- Register/Login

- Browse and enroll in courses

- Watch video lectures and access study material

- Take quizzes and assignments

- Make online payments

- Track learning progress

- Receive certificates and provide ratings/reviews

# Project Scope

## In Scope

- Student registration, login, and profile management

- Course catalog, search, and enrollment functionality

- Video lecture streaming and downloadable study material

- Quiz/assignment creation, submission, and grading

- Online payment gateway integration

- Progress tracking dashboard for students

- Certificate generation and verification

- Instructor course management tools

- Admin panel for user, course, and report management

- Web and mobile app deployment

## Out of Scope

- Offline/desktop-only course delivery

- Third-party course marketplace integrations (Phase 1)

- Live proctored examination system (future release)

- Multi-language content translation (future release)

## Project Objectives (SMART)

| Objective | Target |
| --- | --- |
| Launch MVP with core student/instructor modules | Within 5 months |
| Support concurrent users at launch | 10,000 concurrent users |
| Payment success rate | 99.5% or higher |
| System uptime post-launch | 99.9% monthly |

# Project Timeline

The project is planned using an Agile delivery approach across five sprints/phases, spanning approximately 20 weeks (5 months).

| Phase | Activities | Duration | Milestone |
| --- | --- | --- | --- |
| Phase 1: Initiation & Planning | Requirement gathering, feasibility study, project charter, SRS | Weeks 1–2 | Project plan approved |
| Phase 2: Design | UI/UX design, database design, architecture & API design | Weeks 3–5 | Design sign-off |
| Phase 3: Development | Login, course, payment, and certification modules built in sprints | Weeks 6–13 | Core modules complete |
| Phase 4: Testing | Unit, integration, system, and UAT testing | Weeks 14–16 | UAT sign-off |
| Phase 5: Deployment & Launch | Cloud deployment, mobile app release, go-live | Weeks 17–18 | Production launch |
| Phase 6: Post-Launch Support | Monitoring, bug fixes, feedback collection | Weeks 19–20 | Stabilization complete |

## High-Level Milestone Chart

Project Kickoff (Week 1)

↓

Requirements & Design Signed Off (Week 5)

↓

Core Development Complete (Week 13)

↓

Testing & UAT Complete (Week 16)

↓

Go-Live (Week 18)

↓

Stabilization & Handover (Week 20)

# Team Roles and Responsibilities

| Role | Count | Key Responsibilities |
| --- | --- | --- |
| Project Manager | 1 | Overall planning, scheduling, stakeholder communication, risk tracking |
| Business Analyst | 1 | Requirement elicitation, SRS documentation, backlog grooming |
| UI/UX Designer | 1 | Wireframes, prototypes, user experience design |
| Solution Architect | 1 | System architecture, technology selection, API design |
| Frontend Developers | 2 | React-based web and mobile interface development |
| Backend Developers | 2 | Node.js/Java APIs, business logic, payment integration |
| Database Administrator | 1 | Database schema design, optimization, and maintenance |
| QA/Test Engineers | 2 | Test case design, unit/integration/system/UAT testing |
| DevOps Engineer | 1 | CI/CD pipeline, cloud deployment, monitoring |
| Scrum Master | 1 | Facilitates sprint ceremonies, removes impediments |

## Organizational Structure

Project Sponsor

↓

Project Manager

↓

Scrum Master

↓

Development Team (Frontend / Backend / DBA / DevOps / QA)

# Resource Allocation

| Resource Type | Details |
| --- | --- |
| Human Resources | 12 team members across design, development, QA, and DevOps |
| Hardware | Development workstations, staging servers |
| Software/Tools | Jira, Git, Figma, Jenkins/GitHub Actions, Slack |
| Cloud Infrastructure | AWS/Azure/Google Cloud for hosting and video streaming |
| Budget | Allocated across design, development, testing, and cloud costs |

# Risk Management Plan

| Risk | Impact | Mitigation Strategy |
| --- | --- | --- |
| Scope creep due to changing requirements | High | Agile sprints with change-control review at sprint planning |
| Payment gateway integration delays | Medium | Early vendor engagement and sandbox testing |
| Video streaming performance issues | High | Load testing and CDN-based content delivery |
| Key resource unavailability | Medium | Cross-training and documented handover processes |
| Security/data privacy breach | High | Regular security audits and encrypted data storage |

# Deliverables Summary

| Phase | Deliverable |
| --- | --- |
| Initiation & Planning | Project Charter, Software Project Plan, SRS |
| Design | UML Diagrams, Database Schema, UI Mockups |
| Development | Working software increments per sprint |
| Testing | Test Plan, Test Cases, UAT Sign-off Report |
| Deployment | Deployed Application, Release Notes |
| Post-Launch | Maintenance Log, Support Documentation |

# Results

- A structured project plan clarifies scope boundaries, preventing uncontrolled feature additions.

- A phase-wise Agile timeline of 20 weeks enables predictable delivery of the LMS.

- Clearly defined team roles reduce ambiguity and improve accountability across the project.

- Proactive risk management minimizes the impact of common LMS project risks such as scalability and payment integration issues.

# Conclusion

This case study demonstrates that a well-structured software project plan — with a clearly defined scope, a realistic phase-wise timeline, and well-assigned team roles — is essential for the successful delivery of a real-world application such as an Online Learning Management System. By combining Agile planning practices with disciplined resource allocation and risk management, the project team can deliver a scalable, reliable, and user-friendly LMS within the planned timeline and budget.